# Comprehensive Development Plan: Internship Program Management Application

Overall Objective: To develop the Minimum Viable Product (MVP) of a web application for managing internship programs, focusing on the Dynamic Activity Checklist, documents, and monitoring.

Frontend Technology Stack: React.js Team: 4 Interns

TOTAL DURATION: 3 WEEKS (15 Working Days)

## Introduction and Problem Statement

The current management of internship programs, particularly those supported by European initiatives like Erasmus+, relies heavily on manual processes, disparate documents (PDFs, CVs, evaluation sheets), and fragmented communication channels between the host organization (Yudaya S.L.), the sending partner (Mechatronics Technical School N° 1, Poland), and the interns.

Problem: This manual system introduces risk of error, lack of real-time transparency regarding intern progress (tasks and commitment), and delays in final certification (Europass Mobility).

Solution: This project aims to build a centralized web application to digitize and automate the entire internship lifecycle. The application will serve as a single source of truth for documentation, schedules, and real-time activity tracking via a dynamic checklist, ensuring clear monitoring and timely program closure.

## PROJECT OVERVIEW TIMELINE (3 Weeks)

The project is divided into three concurrent and high-intensity phases.

| Module | Week 1 | Week 2 | Week 3 |
| --- | --- | --- | --- |
| Backend Core (Intern 1) | Models and Security (CRUD APIs) | Weekly Monitoring APIs | Integration Tests with Frontend |
| Backend Logic (Intern 2) | Checklist and Document Models | Checklist APIs and Schedule Module | Optimization and API Documentation |

| Frontend UI (Intern 3) | Wireframes, React Setup, and Authentication Views | HR Dashboard and Intern Profile | KEY Operational Checklist View |
| --- | --- | --- | --- |
| QA/Support (Intern 4) | DevOps/Git Setup, Test Cases | Continuous API Testing (B1/B2) | Compliance Testing (Functions) and Deployment |

# FUNCTIONAL DEVELOPMENT OF THE MVP (EXTENDED DETAIL)

The project must meet the needs of three main user roles:

  - Functionalities per User Role

| Role | Key Views | Required Functionalities |
| --- | --- | --- |
| PARTICIPANT (Intern) | Login, My Profile, Activity Checklist, Document Upload, Schedule Module. | * Task Tracking: View list of assigned tasks (Section 2 of the Agreement) and mark them as In Progress or Completed. * Documentation: Upload CV and Final Internship Report. * Communication: View contact details for supervisors. * Schedule: Register daily check-in and check-out times. |
| SUPERVISOR (Company/Sending Tutor) | Login, List of Assigned Participants, Intern Profile. | * Weekly Monitoring: Conduct the "Evaluation of the participant's internship review at least once a week" (SEGUIMIENTO_SEMANAL table). * View Checklist: Monitor the intern's task progress in real-time. * |

|  |  | Documents: Download CVs and Final Reports. * Final Approval: Mark the internship program as 'Completed and Approved' using the tutor_final_approval field once the internship is finished. |
| --- | --- | --- |
| HR / Coordination | Login, General Dashboard, Reports Module, Program Administration. | * Master Management: Create new PROGRAMA_PRACTICAS, add ACTIVIDAD (tasks) to those programs, and assign Supervisors. * Reports: View the general status of all interns (e.g., Internships ending this month). * Final Documents: Issue and register the Internship Certificate (Europass Mobility). |

  - Detailed Checklist Module Flow (KEY)

This is the central module that must be fully operational by the end of Week 3.

### Backend (Intern 2)

      - Initial Load: The complete list of the 23 "Functions to be performed" (Section 2) is loaded into the ACTIVIDAD table.

      - Automatic Assignment: When a new PARTICIPANTE is created and assigned a PROGRAMA_PRACTICAS, the Backend must automatically generate 23 records in the PARTICIPANTE_ACTIVIDAD table for that intern, with the status field initialized to "Pending".

      - Read API: Create a secure endpoint (GET /api/intern/{id}/checklist) that returns the task name, description, and its status.

      - Update API: Create an endpoint (POST /api/intern/checklist/{id_relation}/update) that allows the intern to update the status (e.g., from "Pending" to "Completed").

### Frontend (Intern 3) - Using React.js

      - Setup: Use a modern React component structure (Functional Components and Hooks).

      - View: A single clean and responsive view for the intern with filters by activity type (Technical, Safety, Soft Skills). Use useState to manage task status.

      - Interaction: Each task must have an associated checkbox that, when checked, calls the

Update API (2.B.1.4) to change the status to "Completed".

      - Tutor Visualization: The Tutor accesses a "read-only" view of the same Checklist to verify progress.

# TASK AND ROLE DISTRIBUTION (WEEKLY ADJUSTMENT)

The distribution remains the same, but tasks must be completed in one-week blocks.

Week 1: Setup and Structure (Database and Authentication)

| Role | Priority Tasks (100% Completion) | Key Intern |
| --- | --- | --- |
| Backend Core | Master Models (Participant, Supervisor, Program). Implementation of Authentication and basic CRUD APIs. | Intern 1 |
| Backend Logic | Task Models (ACTIVITY, PARTICIPANTE_ACTIVIDA D) and Document Models. Initial implementation of the secure file upload system. | Intern 2 |
| Frontend UI | React project setup (Vite/CRA), Wireframe Design, and Development of Login/Registration Views (React Components). | Intern 3 |
| QA/Soporte | Git Configuration and creation of Test Cases based on the 23 "Functions | Intern 4 |

|  | to be performed" from the agreement. |  |
| --- | --- | --- |

Week 2: Business Logic and View Connection

| Role | Priority Tasks (100% Completion) | Key Intern |
| --- | --- | --- |
| Backend Core | Weekly Monitoring APIs (SEGUIMIENTO_SEMANAL). Security and authorization adjustments. | Intern 1 |
| Backend Logic | Checklist APIs (GET/UPDATE) and Schedule Module. Implementation of Automatic Task Assignment. | Intern 2 |
| Frontend UI | Development of React Components for the HR Dashboard and the Intern Profile view. Initial API connection (Data Fetching from Intern 1). | Intern 3 |
| QA/Soporte | Continuous API Testing (Intern 1 and 2). Ensure that the Checklist logic functions in the backend. | Intern 4 |

Week 3: Checklist, Final Tests, and Deployment

| Role | Priority Tasks (100% Completion) | Key Intern |
| --- | --- | --- |
| Backend Core | Frontend Integration Tests. Code optimization. | Intern 1 |

| Backend Logic | Final API Documentation. Support for QA tests. | Intern 2 |
| --- | --- | --- |
| Frontend UI | Implementation and testing of the Checklist View (KEY) using React State/Hooks and the Document Interface. | Intern 3 |
| QA/Soporte | Compliance Testing (UAT). Final Documentation. Deployment to Production. | Intern 4 |

## DATABASE DESIGN (Unchanged)

The database schema remains the same, as it is the minimum logical structure to support the required MVP functionalities.

Master Tables (Core Entities)

| Table | Key Fields (Attributes) | Type | Notes |
| --- | --- | --- | --- |
| PARTICIPANTE | id (PK), full_name, training_sector, sending_partner, program_id (FK), tutor_final_approv al | Various / BOOL | Intern data and final tutor sign-off. |
| SUPERVISOR | id (PK), full_name, email, role_type (Host/Sending) | Various | Tutor data. |
| PROGRAMA_PRA CTICAS | id (PK), program_name, start_date, end_date, host_org_id (FK) | Various | Framework agreement data. |

| ACTIVIDAD | id (PK), program_id (FK), function_descriptio n, activity_type (Technical/Safety/S oft) | Various | Tasks from Section 2 of the agreement (the basis for the checklist). |
| --- | --- | --- | --- |
| DOCUMENTO | id (PK), participant_id (FK), doc_type (CV/Report/etc.), file_path, upload_date | Various | Secure file storage. |

Relationship Tables (Dynamic Checklist and Monitoring)

| Table | Key Fields (Attributes) | Type | Notes |
| --- | --- | --- | --- |
| PARTICIPANTE_A CTIVIDAD | id (PK), participant_id (FK), activity_id (FK) | Various | KEY for the Checklist. |
|  | status | ENUM | (Pending, In Progress, Completed). |
|  | completion_date | DATE |  |
| SEGUIMIENTO_SE MANAL | id (PK), participant_id (FK), tutor_id (FK) | Various | Weekly tutor evaluation (Section 5). |
|  | week_num | INT |  |
|  | tutor_evaluation | TEXT |  |

# APPLICATION WORKFLOW (FLUJO DE TRABAJO DE LA APLICACIÓN)

This section details the complete lifecycle of an internship within the application,

demonstrating the interaction between the three user roles.

- HR/Coordinator (Start ofi the Program)

  - Setup: HR creates a new PROGRAMA_PRACTICAS and defines the master list of ACTIVIDAD (tasks) for that program (Backend Core/Logic: Interns 1 & 2).

  - Assignment: HR registers a new PARTICIPANTE (Intern) and links them to the Program and their SUPERVISOR (Tutor).

  - Automatic Task Generation (KEY STEP): The Backend automatically generates the PARTICIPANTE_ACTIVIDAD records (the checklist) for the new intern.

- Participant (Daily/Weekly Activity)

  - Login: The intern logs in and accesses their Activity Checklist (Frontend: Intern 3).

  - Task Tracking: As tasks from the "Functions to be performed" list are completed, the intern marks the respective items on the checklist as 'Completed', sending an update to the Backend (Intern 2 API).

  - Scheduling: The intern registers their daily check-in and check-out times in the Schedule Module.

  - Documentation: The intern uploads their CV and, later, their Final Report.

- Supervisor (Weekly Monitoring)

  - Monitoring: The Tutor logs in and views the Intern's profile, specifically the Activity Checklist, to see the status updated in real-time.

  - Weekly Evaluation: The Tutor fills out the weekly SEGUIMIENTO_SEMANAL evaluation, rating the intern's progress and providing feedback (Backend Core: Intern 1 API).

  - Documentation Review: The Tutor downloads and reviews the intern's Final Report.

- Program Closure (Final Approval)

  - Final Vetting: Once all tasks are marked as 'Completed' and the Tutor has reviewed the final documents and aflendance records.

  - Tutor Sign-Off: The Supervisor updates the PARTICIPANTE record by sefling the

tutor_final_approval field to True. This action finalizes the internship in the system.

  - HR Action: HR uses the reports module to issue the final Certificate of Practices (Europass Mobility) based on the completed checklist and final approval.

## DATABASE DESIGN (Unchanged)

The database schema remains the same, as it is the minimum logical structure to support the required MVP functionalities.

Master Tables (Core Entities)

| Table | Key Fields | Type | Notes |
| --- | --- | --- | --- |

|  | (Attributes) |  |  |
| --- | --- | --- | --- |
| PARTICIPANTE | id (PK), full_name, training_sector, sending_partner, program_id (FK), tutor_final_approv al | Various / BOOL | Intern data and final tutor sign-off. |
| SUPERVISOR | id (PK), full_name, email, role_type (Host/Sending) | Various | Tutor data. |
| PROGRAMA_PRA CTICAS | id (PK), program_name, start_date, end_date, host_org_id (FK) | Various | Framework agreement data. |
| ACTIVIDAD | id (PK), program_id (FK), function_descriptio n, activity_type (Technical/Safety/S oft) | Various | Tasks from Section 2 of the agreement (the basis for the checklist). |
| DOCUMENTO | id (PK), participant_id (FK), doc_type (CV/Report/etc.), file_path, upload_date | Various | Secure file storage. |

Relationship Tables (Dynamic Checklist and Monitoring)

| Table | Key Fields (Attributes) | Type | Notes |
| --- | --- | --- | --- |
| PARTICIPANTE_A CTIVIDAD | id (PK), participant_id (FK), activity_id (FK) | Various | KEY for the Checklist. |

|  | status | ENUM | (Pending, In Progress, Completed). |
| --- | --- | --- | --- |
|  | completion_date | DATE |  |
| SEGUIMIENTO_SE MANAL | id (PK), participant_id (FK), tutor_id (FK) | Various | Weekly tutor evaluation (Section 5). |
|  | week_num | INT |  |
|  | tutor_evaluation | TEXT |  |